# BAYNARDS ZAMBIA TRUST

# REPORT TO DONORS

# ACHIEVEMENTS AND CHALLENGES OF THE ZRDF

# PROGRAMME IN 2017

# JANUARY 2018

THANK YOU The progress in 2017 described below was only achieved as a result of the generous financial support of all our donors.  The BZT Trustees are very grateful to donors for your confidence in the work that BZT’s Zambian partner, ZRDF, is achieving working closely with fifteen rural communities of South Mkushi, a population estimated at 90,000 in an area of 4,500 square miles.

2017 OVERVIEW

During the three years 2014/16, the holistic approach of ZRDF embraced: improved income generation through agriculture, with a focus on introducing the planting and harvesting of soya beans; a major expansion in the number of Savings and Internal Lending Communities (SILC), which are in essence village banks, contributing to economic well-being and to increased participation of women.

Access to education was improved with the provision of new facilities, including 17 new teachers’ houses, 6 new teaching blocks (each with three classrooms) and 30 new toilets, as well as the provision of badly needed educational materials.  As a result, there were 
71 trained teachers across 15 schools at December 2016, compared to 39 three years earlier. The HIV and AIDS work raised awareness and those individuals living with HIV were tested and initiated in ART treatment.

These three years proved that the ZRDF approach had been a real success with an extremely high level of collaboration between ZRDF and the people they are supporting.  Donors have commented, and ZRDF agrees, that this holistic ZRDF approach is a successful model that could be replicated by ZRDF and by other agencies elsewhere in Zambia and indeed in other developing countries.

Building on the success of the previous three years, and after extensive consultation with and through ZRDF, with both the existing and the potential New Communities, combined with BZT’s own experience and advice from several informed donors, a 2017-19 three-year plan was agreed and implemented from January 2017.

The major development in the 2017/19 plan was to commence work in five New Communities (described on the map as “proposed New Communities”). They are more physically isolated than the other ZRDF communities and exhibit severe evidence of deprivation with mono-cropping of maize and very low incomes.  Three communities had no clean water and had mud and wattle school facilities with no trained teachers, most with no teaching materials and all suffering from limited access to very distant medical facilities, with the sick travelling long distances by ox cart.  All the community leaders demonstrated an eagerness to work with ZRDF, aspiring to make the progress achieved at the earlier ZRDF communities.

The objectives for 2017 agreed between BZT and ZRDF were:

- ZRDF to continue the interventions of crop diversification, economic empowerment (SILC), education, HIV and AIDS and community capacity building in the Sakala communities and in the New Communities.  The targets and results of which are shown in the table below.

- Appointing new ZRDF programme managers to underpin the activities in the field.

- Establishing training for subsistence farmers in their fields to improve yields by establishing the first of two demonstration sites.

- Diversifying via a pilot into beekeeping and honey production.

- Hiring an education officer to facilitate the exchange of best practices in the classroom and thereby improve teaching standards.

- Investing further in expertise which will enable BZT to enhance the reporting of impacts as well as outputs.

PROGRESS AGAINST PLANNED TARGETS IN 2017

| ACTIVITY | TARGET | ACTUAL | COMMENT |
| --- | --- | --- | --- |
| AGRICULTURE |  |  |  |
| Smallholder farmer group forums conducted | 12 | 29 | In both Sakala and the New Communities, ZRDF is encouraging a change in farmer mind-set to consider farming as a business and not just producing crops for home consumption; also encouraging the approach of Conservation Agriculture. |
| Agricultural and producer groups formed and strengthened for soya bean production | 6 | 13 | Producer groups were strengthened through training in soya bean production, entrepreneurship, agri-business training and four new producer groups were formed. |
| Linkages established to strengthen agricultural groups | 6 | 17 | Linkages were established with seed, fertiliser, agri-companies and government departments. |
| Promotions conducted in the use of improved varieties of high value crops Farmers reached with marketing information of high value crops through farmer forums | 6 350 | 18 1,360 | Promotions were conducted in high value crops (sun-hemp, cow peas, ground nuts, sunflower, sorghum, soya beans and orange maize) at the demonstration site in the Sakala and New Communities. |
| Number of new farmers growing soya beans | 200 | 135 | Currently 505 farmers are growing soya beans from both Sakala and New Communities; of these 135 were new farmers recruited in 2017. |
| Number of farmers breeding goats | 60 | 80 | There are 9 groups with 160 goats. |
| Farmers selected for bee keeping and honey production | 50 | 25 | 150 farmers were trained in bee production. 250 hives were procured and each farmer received 10 hives rather than the original plan of 5 to improve the economics. |
| EDUCATION |  |  |  |
| Construction of 1x3 classroom block | 1 | 1 | Classroom block at Mitwe was completed in December 2017. |
| Schools supported with educational materials | 5 | 4 | Objective is to reduce textbook to pupil ratio to 1:2 in 5 subjects in grades 5 to 7 (Mitwe, Boole, Kamimbya, Kalubula). |
| Teacher’s house to be constructed in the New Communities | 2 | 7 | 3 at Boole, 2 at Minsundu and 2 at Mitwe. |
| Construction of pupil hand washing facilities | 3 | 3 | Boole, Minsundu and Mitwe. |
| Pupil toilets | 6 | 6 | Two at each school, Boole, Mitwe and Minsundu. |
| Staff Toilets | 0 | 2 | One at each Boole and Minsindu. |
| ECONOMIC EMPOWERMENT |  |  |  |
| Community members participating in the SILC programme | 1,000 | 1,521 | These are the number of direct beneficiaries who were reached and are saving in SILC Groups. |
| Formation of new SILC groups. | 40 | 41 | The target was achieved due to the increased number of SILC field agents trained and their active participation within their respective communities. It was also due to the entrepreneurship training that took place in all the communities. |
| Training of SILC field agents | 20 | 15 | 15 field agents were trained to support all the increased number of groups formed in 2017. |
| HIV & AIDS |  |  |  |
| Community members reached with HIV and AIDS awareness messages | 4,000 | 8,857 | The target was exceeded as a result of the training of new care givers as well as the collaboration with the Ministry of Health during commemoration of national events. |
| In school youths reached with SRH (Sexual Reproductive Health) and HIV & AIDS information services | 4,000 | 3,777 | Mobile health services were provided in schools as well as HIV counselling and testing. |
| PLHIV newly initiated on ART treatment | 200 | 249 | Focus group discussions and an increase of trained care givers helped in meeting the target. |
| Trained care givers | 20 | 45 | 45 care givers were trained and supported, 25 were newly trained. |
| COMMUNITY CAPACITY BUILDING |  |  |  |
| CBOs formed, operational and being registered | 3 | 4 | Four CBOs were formed and are functional with registration in process. |
| Annual/Mid term reviews with CBOs | 12 | 15 | Reviewed projects, activities and performance as well as phase out strategy. |

PROGRAMME MANAGERS

In addition to Finance, Brandy Mungaila (the ZRDF Director) has strengthened his team and now has reporting to him:

- Senior Strategy and Monitoring Officer

- Senior Programme Officer

- Livelihoods and Food Security Programme Officer

- SILC Programme Officer

- Education Programme Officer (see below)

- HIV & AIDS Programme Officer.

This means that there is now a dedicated ZRDF manager for each of the areas BZT supports. This is expected to significantly improve the delivery of BZT’s investment on the ground for both communities and individuals, as well as providing more accurate reporting and analysis of data.

DEMONSTRATION SITES

The preparation of the first demonstration site at Kalabula (one of the more accessible of the New Communities) is well advanced. A successful farmer has donated a four-hectare plot, half of which had been farmed and other half un-cleared land. The latter was cleared by the end of December, funded by BZT. The concept is that subsistence farmers will be invited for training days where they will learn about new crops (e.g. sunflowers, cow peas) as well as current crops of soya and maize and the differing ways of managing them to obtain higher yields. This will be done in conjunction with commercial companies supplying seeds, fertilisers and other inputs who have confirmed in writing their willingness to participate.  ZRDF has hired a consultant to advise on the size of plots and will run the training days. Planting of a variety of crops commenced in the last quarter of 2017.

BEE KEEPING AND HONEY MAKING

2017 was the first year of this scheme managed by ZRDF but in partnership with a commercial company, which has philanthropic as well as financial objectives, and which buys honey from rural farmers across Zambia.

As a pilot, 250 Chinese manufactured hives have been acquired at a cost of $20 each and ten hives have been provided (50% of the cost as a loan) to each of the 25 farmers in areas where the Miombo tree grows, much favoured by bees. Bees settle in areas of low human disturbance so the New Communities have ideal sites. The commercial company will collect the honey twice a year. Each farmer is then paid in the field and when ultimately the honey is sold by the company each group of famers will also receive a share of the profits. It is planned that if the pilot is successful many more farmers will participate as 150 farmers have already involved in extensive bee keeping training.

TEACHING STANDARDS

The new Education Programme Officer (a very experienced educator and retired head) organised a gathering of the Head Teachers of the 15 schools supported by ZRDF. It was encouraging that 13 turned up.

He explained the importance of developing data tools to track progress within a school and for comparative purposes between the schools.

He plans to:

- Compile end of year test results and pick ten pupils for awards

- Encourage schools to form houses for competition purposes

- Hold inter school competitions in numeracy and literacy

- Ask schools to start and intensify maintenance activities

- Propose each school forms at least two after school clubs

- Present awards to deserving pupils, teachers, houses and schools.

As he builds productive relationships with the 15 Head Teachers he will be a critical friend to support their roles.

IMPACT REPORTING

The majority of peasant farmers (300) benefiting from the soya loans have had their household incomes increased which resulted in the purchase of mechanised farming tools, as opposed to traditional farming implements such as hand hoes, for cultivation of their land. There has been a notable improvement in the nutrition at household level with daily meals increased from formerly a low level. The farmers have greater knowledge on new farming technologies such as Conservation Farming which has huge benefits in terms of productivity.

Community Based Organisations were formed which supported ZRDF in the four thematic areas and whose members were trained in leadership skills. This is evidenced through the mobilisation of the communities to provide upfront building materials such as bricks, stones and sand to build a 1 x 3 classroom block, 7 teachers’ houses, 15 VIP toilets and 2 hand washing facilities.

As a result of the community based volunteer support, made possible by the ZRDF training, there has been a huge impact in the number of people who have accessed ART treatment from 150 to 1200 and who are currently living quality lives.

Women have successfully advanced from the concept of a micro loan to saving their own money through a village bank (SILC – Savings and Internal Lending Communities). Currently, there are 113 SILC groups with 1521 members. Great successes have been achieved with some groups saving up to Kwacha 48,000 (£4,000). Profits from businesses started by loans by the members of these groups have made investments in the home, and in addition these women are able to travel to other towns. The savings of their own money has resulted in more commitment and ownership as compared to the provision of loans.

As a result of the construction of a sustainable classroom block and 7 teachers’ houses, the government have appointed trained teachers to these schools. This has significantly improved the quality of education provided to the pupils, together with educational materials provided by BZT. As a result, pupil numbers have doubled in many of these schools.

PLANS FOR 2018

Livelihoods and Food Security

- Develop the new demonstration site for purposes of learning and sharing of new agricultural practices from different stakeholders for improved productivity aimed at reaching  500 farmers

- Continue to promote and introduce new high value crops for 200 farmers.

- Conduct market research and establish linkages to help 500 farmers with marketing of crops for the 2017/18 farming season

- Empower 50 farmers with improved bee keeping skills for enhanced honey production.

SILC

- Improve financial literacy and entrepreneurship skills of 1500 members of SILC groups

- 40 new SILC Groups to be formed and provided with technical support.

Institutional Support

- Improve the management of 9 CBOs and facilitate the legal registered constitutions.

HIV&AIDS

- 7,000 community members to be reached with HIV and AIDS awareness prevention messages

- 4,000 young people in school to be reached with SRH information services

- 3,000 people reached and provided with HIV prevention, treatment and support programmes through mobile health services

- Improve the quality and prolong the lives of 60 PLHIV through palliative care

- Enhance disclosure and male involvement through focus group discussions to support ART adherence and prevention information

- 250 PLHIV newly initiated on ART treatment

- 50 HIV positive Children (below 15yrs) provided with ART services.

Educational Support

- Enhance quality education participation and results among 5,000 pupils through holding 45 award ceremonies, tests, quizzes and 3 spelling competitions and providing educational materials to schools

- Enhance pupils’ nutrition through support to 3 schools through school feeding programmes targeting 600 pupils.

- Improve teachers’ teaching skills for 71 Teachers through continued professional development meetings and head teachers’ gatherings.

- Continue with Tertiary Education bursaries for 5 OVC

ZAMBIAN CURRENCY

During 2016 the value of the Kwacha to the Pound fluctuated wildly between £1 = 11.9 Kwacha and £1 = 16.9 Kwacha. The average exchange rate on the BZT remittances to Zambia was £1 = 14 Kwacha.

During 2017 the rate was relatively stable around £1 = 11.75 Kwacha,although in the last few months of the year the Kwacha helpfully weakened to £1 = 13.6 Kwacha. The average rate achieved was £1 = 12.2 Kwacha. If the 2017 average rate had been the same as 2016 BZT could have sent an additional 550,000 Kwacha to ZRDF or 15%.

BZT AND ZRDF

There have been no changes to the Trustee Board of BZT, which has met three times during the year. BZT Trustees visited Zambia in April and September 2017 and these were preceded by a visit of Brandy Mungaila to the UK in November 2016 to finalise the 2017 budget.

FUNDRAISING

The BZT Trustees are extremely grateful to the donors who have funded the work in 2017 which include:

-  The British & Foreign School Society

-  Hazelhurst Trust

- Hilden Charitable Fund

- Jamma International

- Maitri Trust

- Guernsey Overseas Aid and Development Commission

- Mercury Phoenix Trust

- MPM Charitable Trust

- A&N Fergusson Charitable Settlement

- PF Charitable Trust

- Strathspey Charitable Trust

- Savills

- Tula Trust

- BZT Trustees

- And numerous other individuals

- Many contributors to the Big Give

ZRDF Fundraising

ZRDF has employed a full time member of staff whose core business is to create partnerships and fundraising to expand the sources of funding beyond just BZT. ZRDF successfully negotiated with the Egmont Trust to directly support part of the ZRDF programme.

During 2017, ZRDF has met a total of 55 organizations covering the four thematic areas in order to create partnerships or tap into their funding sources. A total of 9 proposals were submitted to potential donors.

At the same time, ZRDF has been able to secure 15 different types of HIV & AIDS tool kits for improved programme delivery, a signed memorandum of understanding for the continued supply of condoms and information promoting savings and loans at no cost to ZRDF.  Even though financial benefits have not yet been recognised, it is evident that ZRDF has become more visible to other organisations, both locally and for possible strategic partnerships.

FINANCE: BZT

During 2017 BZT has remitted £304,000 to Zambia which realised Zambian Kwacha 3.7 million at an average exchange rate of £1 = 12.2 Kwacha.

At 31st December 2017 BZT had £30,000 of cash in the bank.

As donors are aware, all UK and travel costs are funded personally by BZT Trustees, so no such costs, which totalled £21,000 in the year, were a burden to the ZRDF programme.

Zambian inflation is currently around 6% pa. It did peak at 20% in 2015/16.

FINANCE: ZRDF

The Appendix contains a breakdown of the ZRDF spending in 2017.

# CONCLUSION

# BZT Trustees believe that this first year of the new 2017/19 three year programme has, as demonstrated above, largely met objectives agreed a year ago between ZRDF and BZT.

# The positive and active participation of the members of the New Communities has been key.

# The Trustees very much hope that existing donors will feel motivated to continue their much-valued support.

# Thank you.

# Robert Napier

# Trustee

# January 2018

APPENDIX 1

ANALYSIS OF 2017 ZRDF EXPENDITURE

Kwacha ‘000

DIRECT PROGRAMMES COSTS (EXCL STAFF)

Livelihoods and food security		315

Economic empowerment 			  81

HIV and AIDS                  		          145

Institutional strengthening			 60

Bursaries					 72

673

SCHOOL INFRASTRUCTURE

Boole						444

Mitwe						639

Minsundu					322

Other 						  26

1,431

EDUCATIONAL MATERIALS					 89

MASANSA FIELD OFFICE COSTS

Staff costs					1,022

Staff training and evaluation           	   199

Transport                   			   153

Administration 				   168

1,542

TOTAL	Kwacha 					K 3,735,000

Pounds					£306,000